## Planning
Activities
Planning stage
Execution stage
Reporting stage
# | Activities | Months on 2017
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Empirical study - reporting (Phase I, Activity D) result mapping along with inspection technique draft | bar: Months on 2017 Jan
2 | Systematic Literature Review - planning search query construction and protocol review | bar: Months on 2017 Jan
3 | Systematic Literature Review - execution abstracts reading, paper selection, full reading | bar: Months on 2017 Feb
4 | Systematic Literature Review - reporting results mapping, monography writing | bar: Months on 2017 Mar
5 | Inspection technique proposal and validation with a BDD expert reflect monography attributed maping on inspection technique draft after validatio | bar: Months on 2017 Mar to Months on 2017 Apr
6 | Practitioners Interview - planning exemples mapping and protocol review presentation | bar: Months on 2017 Apr to Months on 2017 May
7 | Practitioners Interview - execution interviews execution, progress report presentation | bar: Months on 2017 Jun to Months on 2017 Jul
8 | Practitioners Interview - reporting results mapping | bar: Months on 2017 Aug to Months on 2017 Sep
9 | Quality inspection final changes reflect interviews maping on it, justify each question and changes | bar: Months on 2017 Oct
10 | Specialist Interviews to evaluate the proposed quality inspection justify good/bad decisions and final validations | bar: Months on 2017 Nov
11 | Dissertation final report results mapping, dissertation writing | bar: Months on 2017 Aug to Months on 2017 Dec
Phase 1 period - 2016 to Jan/2017 | bar: Months on 2017 Jan
Phase 2 period - Jan to Apr | bar: Months on 2017 Jan to Months on 2017 Apr
Phase 3 period - May to Dec | bar: Months on 2017 Apr to Months on 2017 Dec

## Planning (2)
Activities
Planning stage
Execution stage
Reporting stage
# | Activities | Months on 2017
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Empirical study - reporting (Phase 1, Activity D) | bar: Months on 2017 Jan
2 | Systematic Literature Review - planning (Phase 2, Activity E) | bar: Months on 2017 Jan
3 | Systematic Literature Review - execution (Phase 2, Activity E) | bar: Months on 2017 Feb
4 | Systematic Literature Review - reporting (Phase 2, Activity E) | bar: Months on 2017 Mar
5 | Inspection technique proposal and validation with a BDD expert (Phase 2, Activity F) | bar: Months on 2017 Mar to Months on 2017 Apr
6 | Practitioners Interview - planning (Phase 3, Activity G) | bar: Months on 2017 Apr to Months on 2017 May
7 | Practitioners Interview - execution (Phase 3, Activity G) | bar: Months on 2017 Jun to Months on 2017 Jul
8 | Practitioners Interview - reporting (Phase 3, Activity G) | bar: Months on 2017 Aug to Months on 2017 Sep
9 | Quality inspection final changes (Phase 3, Activity H) | bar: Months on 2017 Oct
10 | Specialist Interviews to evaluate the proposed quality inspection (Phase 3, Activity I) | bar: Months on 2017 Nov
11 | Dissertation final report (Phase 3, Activity J) | bar: Months on 2017 Aug to Months on 2017 Dec
Phase 1 period - 2016 to Jan/2017 | bar: Months on 2017 Jan
Phase 2 period - Jan to Apr | bar: Months on 2017 Jan to Months on 2017 Apr
Phase 3 period - May to Dec | bar: Months on 2017 Apr to Months on 2017 Dec