## Planning
Activities
Planning stage
Execution stage
Reporting stage
Activities | Months on 2017
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Systematic Literature Review - planning search query construction and protocol review | bar: Months on 2017 Jan
Systematic Literature Review - execution abstracts reading, paper selection, full reading | bar: Months on 2017 Feb
Systematic Literature Review - reporting results mapping, monography writing | bar: Months on 2017 Mar
Quality inspection proposal reflect monography maping on it, justify each question and changes | bar: Months on 2017 Mar to Months on 2017 Apr
Practitioners Interview - planning exemples mapping and protocol review | bar: Months on 2017 Apr to Months on 2017 May
Practitioners Interview - execution interviews execution | bar: Months on 2017 Jun to Months on 2017 Jul
Practitioners Interview - reporting results mapping, start of dissertation writing | bar: Months on 2017 Aug to Months on 2017 Sep
Quality inspection final changes reflect interviews maping on it, justify each question and changes | bar: Months on 2017 Oct
Specialist Interviews to evaluate the proposed quality inspection justify good/bad decisions and final validations | bar: Months on 2017 Nov
Dissertation final report results mapping, end of dissertation writing | bar: Months on 2017 Dec
Phase 2 period - Jan to Apr | bar: Months on 2017 Jan to Months on 2017 Apr
Phase 3 period - May to Dec | bar: Months on 2017 Apr to Months on 2017 Dec